LottoGuard

Build Execution Plan

Every page, every access level, every layer, every decision — start to finish

Document version: 1.2 — Revised July 8, 2026 (gap-closure review: consent, data export, support escalation, pricing timing, staging timing)

Continues the Architecture Decisions Log from the Consolidated Master Reference (Decisions 1–24) starting at Decision 25. Decisions 32–36 (Section 5) revise the phase sequence agreed in v1.0 based on a same-day walkthrough — Decision 32 explicitly supersedes Decision 29. Every open item is resolved below except where explicitly marked BLOCKED ON external data.

# 0. How This Plan Works

Two kinds of statements appear in this document. A green DECISION box is final — build against it, no further sign-off needed. An amber BLOCKED ON box is the only kind of open item left — it names exactly what external fact is missing and where it gets resolved. Nothing is left in a vague "TBD" state. If it isn't blocked on a real external fact, it's decided.

# 1. Full Sitemap — Every Page, By Role

Organized by application surface. This is the complete page inventory for MVP through Phase 2 (chain/agency). Pages marked (Phase 2) are not built until Section 6's Phase 7.

## 1.1 Shared — Auth & Onboarding

| # | Page | Notes |
| --- | --- | --- |
| 1 | Login | Email/password + 2FA for Manager, Owner, Agency, Office Staff |
| 2 | PIN device login | Shared-tablet login, per employee, cashier + manager use |
| 3 | Signup / organization creation | Owner only — creates the org and first store |
| 4 | Guided onboarding wizard | Store setup, POS config profile capture, first employee, first pack |
| 5 | Password reset | Standard flow |

## 1.2 Cashier App (mobile-first PWA)

| # | Page | Notes |
| --- | --- | --- |
| 6 | PIN login | Device-shared, per-employee |
| 7 | Shift start — pack scan | Batch flow for multiple active packs |
| 8 | Active shift home | Current pack positions only — no other store data visible |
| 9 | Spot-check camera capture | Triggered randomly, in-app camera only, barcode validated client-side |
| 10 | Spot-check confirmation | Hardcoded "Photo submitted successfully" regardless of flag result — Decision 12 |
| 11 | Shift end — closing scan & handover | Multi-pack batch handling |
| 12 | Late-scan override request | Manager-approved, reason logged permanently |

## 1.3 Manager App

| # | Page | Notes |
| --- | --- | --- |
| 13 | Manager dashboard | Today's shifts, active packs, pending reviews |
| 14 | Spot-check review queue | Approve or escalate flagged photos |
| 15 | Pack activation | Receive & activate new pack, barcode scan required |
| 16 | Tally manual entry | Only visible if owner has granted this manager permission |
| 17 | Employee roster (view only) | This store only |
| 18 | Shift handover oversight | Dual sign-off monitoring |
| 19 | Complaint intake form | Feeds the complaint trace tool |

## 1.4 Owner — Single Store

| # | Page | Notes |
| --- | --- | --- |
| 20 | Owner dashboard | Active packs, shift status, employee risk scores at a glance |
| 21 | Real-time alert feed | Silent, one-directional — Decision 12 / silent alerting requirement |
| 22 | Pack detail / history view | Full lifecycle for any pack on demand |
| 23 | Employee management | Add/remove/deactivate, risk score detail |
| 24 | Complaint trace tool | Ticket serial → shift ownership in one query |
| 25 | Incident report generator | One-tap PDF export for HR/legal/insurance |
| 26 | Reconciliation / tally view | Manual, CSV, Bridge, and LSP status unified in one screen |
| 27 | Data source & POS connection status | Bridge app health, LSP status, per-store config profile editor |
| 28 | Spot-check trigger configuration | Within agency-set bounds |
| 29 | Store settings & billing | Subscription, payment method, store profile |

## 1.5 Owner — Multi-Store / Chain (Phase 1 — built alongside single-store, Decision 32)

| # | Page | Notes |
| --- | --- | --- |
| 30 | Network dashboard | All stores simultaneously, one view — data model ready Phase 1, dashboard built Phase 5 (Decision 34) |
| 31 | Cross-store employee pattern view | Same employee flagged across multiple locations — moved to Phase 5, Decision 34 |
| 32 | Store comparison view | Ranked by anomaly frequency |
| 33 | Network reconciliation export | Full chain, one file |
| 34 | Multi-store billing management | Per-store fee rollup |

## 1.6 Agency / Reseller (Phase 1 — internal company use first, Decision 32)

Built in Phase 1 primarily for SmartAI's own use — tracking all client stores, billing, and overviews in one place. External agency/reseller customers use the same role later, no rebuild required.

| # | Page | Notes |
| --- | --- | --- |
| 35 | Agency oversight dashboard | All owners, all stores |
| 36 | Manual spot-check trigger | Any store, any pack, any employee, any time — Decision 13 |
| 37 | Org-wide config bounds editor | Min/max spot-check ranges, delegation limits |
| 38 | Data source assignment | Per store — Decision 24 |
| 39 | Agency billing / commission view | Reseller economics |

## 1.7 Office Staff — Read-Only Analyst (Phase 6, Decision 35)

| # | Page | Notes |
| --- | --- | --- |
| 40 | Read-only reconciliation dashboard | Scoped to granted stores |
| 41 | Report export | CSV/PDF, no edit rights |
| 42 | Anomaly feed (view only) | No acknowledgment/dismissal rights |

## 1.8 Cross-Cutting / System

| # | Page | Notes |
| --- | --- | --- |
| 43 | Notification preferences | SMS/push channel choices per user |
| 44 | Audit log viewer | Owner + Agency only — append-only, immutable |
| 45 | Bridge app installer & setup guide | Linked from page 27, runs on back-office PC, outside the web app |
| 46 | Employee consent interstitial | One-time gate shown at first PIN login (page 6) — Decision 37. Not a nav destination, a blocking screen before shift access is granted. |

# 2. Access & Permissions Matrix

Every capability in the system, mapped against every role. This is the enforceable spec for Supabase RLS policies — anything not marked YES here must be blocked at the database level, not just hidden in the UI.

| Capability | Agency | Owner | Manager | Cashier | Office Staff |
| --- | --- | --- | --- | --- | --- |
| View this store's data | YES | YES | YES (own store) | Own shift only | YES (scoped grant) |
| View other stores' data | YES (all) | YES (own chain only) | NO | NO | NO |
| Manual tally entry | YES (flagged) | YES (flagged) | Only if granted (flagged) | NEVER | NO |
| Trigger spot-check manually | YES (any store) | YES (within bounds) | NO | NO | NO |
| See spot-check flag results | YES | YES (all outcomes) | Assigned queue only | NEVER | NO |
| Configure spot-check bounds | Sets outer bounds | Within agency bounds | Within owner delegation | NO | NO |
| Add / remove employees | NO | YES | NO | NO | NO |
| Export incident reports | YES | YES | NO | NO | Read-only export |
| Billing management | Own commission | YES | NO | NO | NO |
| Edit POS / data source config | Assigns path | Within agency-approved options | NO | NO | NO |
| View audit log | YES | YES (own org) | NO | NO | NO |

DECISION: Enforcement mechanism This matrix is implemented as Supabase Row Level Security policies, not application-layer checks alone — per the existing "Data Isolation (RLS)" rule in Section 9 of the Master Document. A UI restriction without a matching RLS policy is treated as a bug.

# 3. System Architecture — The Layers

Nine layers, physical event to billing. Each layer's job is fixed; only its implementation detail changes per store based on the confidence tier (Appendix A, Section A.7).

| Layer | Responsibility | Key components |
| --- | --- | --- |
| 0. Physical / Field | Where the truth originates | Barcode scans, spot-check photos, POS register, lottery terminal |
| 1. Data Ingestion | Get machine-sourced data into the system, per Decision 24 priority order | LSP scraper, PJR Bridge, CStore Bridge, Email parser, CSV upload, Manual entry (last resort) |
| 2. Core Data Store | System of record | Supabase Postgres + Row Level Security, Supabase Storage (photos), Realtime (live alerts) |
| 3. Correlation Engine | Turns raw data into theft signals | Spot-check selection algorithm, cross-check/gap detection, employee risk scoring, silent-alert dispatch rules |
| 4. Application / API | Business logic surface | Next.js API routes, Supabase Edge Functions |
| 5. Frontend | Every page in Section 1 | Next.js + TypeScript, role-based route guards, PWA for Cashier |
| 6. Auth | Identity & session | Supabase Auth, PIN device-login extension, 2FA for Manager/Owner/Agency |
| 7. Billing | Standalone, never touches core | Stripe — per existing build rule, core product works with billing fully disabled |
| 8. Ops & Monitoring | Keeps everything else honest | Sentry, Better Uptime, Checkly, GitHub Actions CI, Playwright, Semgrep, Dependabot |

# 4. Finalized Tech Stack

No changes from the existing Master Document decision — restated here as final, not proposed.

| Layer | Technology |
| --- | --- |
| Frontend | Next.js + TypeScript |
| Database | Supabase (Postgres + Auth + Storage + Realtime + Edge Functions) |
| Hosting | Vercel |
| Payments | Stripe (billing module only, not core) |
| Desktop Bridge | Electron.js (back-office PC PJR/CStore watcher) |
| Testing | Vitest (unit/integration), Playwright (E2E) |
| CI/CD | GitHub Actions |
| Monitoring | Sentry, Better Uptime, Checkly |

# 5. New Decisions (Continuing the Log — Decision 25 onward)

## Decision 25 — Pilot Store Selection

DECISION: Final The Gilbarco Passport store visited July 7–8, 2026 becomes the design partner / pilot store. Direct register data access is already proven there — it is the lowest-risk starting point for the entire build.

## Decision 26 — Barcode Parser Build Sequencing

DECISION: Final Build barcode SCAN CAPTURE infrastructure now (camera component, ZXing integration, client-side scan validation UI) — this is required regardless of how the ticket-uniqueness question resolves. Build ticket-SERIAL PARSING as a swappable module behind a clean interface, so it can be finalized the moment real ticket barcode data is captured (Appendix A, Section A.9, item 1–2) without blocking the rest of the scan flow.

## Decision 27 — PJR Bridge Priority Moved Up

DECISION: Final — supersedes the original Build Order (Master Document, Section 08) The original plan placed the PJR Bridge app in Phase 7 (Month 4+) as a deferred, higher-risk item. Given it is now validated end-to-end against real Gilbarco Passport data at zero integration cost (Appendix A), it moves to Phase 2 (Weeks 3–4), parallel with the barcode scan engine. It is now one of the least risky components in the build, not one of the riskiest — the schedule should reflect that.

## Decision 28 — LSP Portal Access

DECISION: Final The pilot store owner must obtain LSP login credentials before Phase 4 (Tally & Reconciliation) begins. Action owner: request credentials at the next store visit, alongside the barcode-capture checklist (Appendix A, Section A.9).

## Decision 29 — MVP Scope Cutline

DECISION: Final MVP ships Single-Store Owner + Manager + Cashier roles only (Sitemap Sections 1.1–1.4, pages 1–29). Agency and Multi-Store/Chain views (Sections 1.5–1.7, pages 30–42) are Phase 7, not MVP. This was implied by the original Build Order's Phase 6 vs Phase 7 split — it is now an explicit scope decision rather than an inference.

## Decision 30 — Office Staff Role Timing

DECISION: Final Deferred to Phase 7. Low build complexity, but there is no one to grant read-only access to until there is a paying customer with staff. Building it earlier is wasted surface area.

## Decision 31 — Confidence Tier Default

DECISION: Final Every store's config profile (Appendix A, Section A.7) defaults to the lowest confidence tier at onboarding. Tiers upgrade automatically as each data source is verified working — never manually claimed by an owner or agency. This prevents a store from appearing better-monitored than its actual data supports.

## Decision 32 — Agency & Multi-Store Move to Phase 1 (SUPERSEDES Decision 29)

DECISION: Final Decision 29's MVP scope cutline is revised. Agency (built first for SmartAI's own internal use — company-wide store tracking, billing, overview) and the Multi-Store/Chain data model move into Phase 1, not Phase 7. Reasoning: most targeted future clients are multi-store owners, and an Owner-to-Store relationship that is one-to-many from day one is cheap to build correctly now and expensive to retrofit onto a single-store-only schema later. The single-store Owner/Manager/Cashier experience is unaffected — it is simply built on a schema that already supports multiple stores per owner.

## Decision 33 — Ops Tooling Sequencing

DECISION: Final Doppler is removed from the plan — Vercel's built-in environment variable management is sufficient at current team size. Semgrep and Dependabot move into Phase 0 (cheap to wire up once, at repo creation, and then they run themselves). Sentry, Better Uptime, and Checkly are deliberately NOT set up in Phase 0 — each is added at the point in the build where it has something real to monitor: Sentry in Phase 1 (once real auth and real users — starting with internal Agency use — exist), Checkly in Phase 3 (once the spot-check selection algorithm gives it real business logic to check), Better Uptime in Phase 6 (immediately before the pilot store goes live in production).

## Decision 34 — Cross-Store Employee Pattern Detection Timing

DECISION: Final Moves from Phase 7 to Phase 5. Its two dependencies — employee risk scoring and the multi-store data model — are both satisfied earlier now that multi-store moved into Phase 1 (Decision 32) and risk scoring is built in Phase 5. There is no remaining reason to defer this to Month 4+.

## Decision 35 — Office Staff Role Timing (SUPERSEDES Decision 30)

DECISION: Final Moves from Phase 7 to Phase 6. Multi-store owners — now the explicit target audience per Decision 32 — are more likely to have back-office staff who need read-only access before launch, not four months after.

## Decision 36 — Phase 1 Scope Acknowledgment

DECISION: Final Phase 1 is now materially larger than originally scoped in v1.0 — full multi-tenant schema, Agency role, and the internal overview dashboard, not just single-store foundation. This is a deliberate tradeoff, chosen explicitly over building single-store first and retrofitting multi-tenancy later: correct data shape once, in exchange for a later first pilot demo. Phase 1's timeline moves from Weeks 1–2 to Weeks 1–3 to reflect this; every subsequent phase shifts by one week (Section 6).

## Decision 37 — Employee Privacy Consent Flow

DECISION: Final Owner acknowledges monitoring at onboarding (checkbox, ToS language) AND each employee sees a one-time consent interstitial at their first PIN login (Sitemap page 46) before shift access is granted. Rationale: a one-tap, timestamped employee acknowledgment is real evidence in a dispute — consistent with the product's existing evidence-first philosophy (audit trail, complaint trace, incident reports). An owner-only checkbox that no employee ever sees protects the owner alone; this protects both.

## Decision 38 — Data Export on Cancellation

DECISION: Final Manual for now, not self-serve. On cancellation, the owner emails Farheen directly and she handles the export personally. Revisit as a self-serve automated flow once support volume makes manual handling impractical — not needed at pilot/early-customer scale.

## Decision 39 — Bridge App Outage Escalation

DECISION: Final Both channels, not one. The Owner sees a live status banner in the Data Source & POS Connection Status page (Sitemap page 27) on any Bridge outage, AND Farheen is paged directly (SMS/call via Better Uptime) on the same event. No silent failures, and no single point of missed awareness.

## Decision 40 — Pricing Deferred

DECISION: Final — deliberately deferred, not blocked Real pricing (Stripe plan configuration, the specific $49/$120/agency-tier numbers from the Competitive Analysis) is decided after the pilot store is running well, not before. This is a conscious sequencing choice, not an unresolved dependency — Phase 5's billing work proceeds using placeholder/test pricing until a real decision is made. Revisit explicitly before any paying customer beyond the pilot is onboarded.

## Decision 41 — Staging Environment Timing (SUPERSEDES the Phase 0 ops list default)

DECISION: Final Staging Supabase setup moves out of Phase 0 and into Phase 6, immediately before the pilot store goes live. Rationale: staging protects production traffic from risky migrations — there is no production traffic to protect until launch week, so standing it up earlier only slows Phase 0 down for a risk that doesn't exist yet. The staging rules themselves (Ops Tracker Section 14 — always migrate to staging before production) are unchanged, just deferred to when they start mattering.

# 6. Unified Build Sequence — Start to Finish

Revised per Decisions 32–36. Combines the original Build Order, the Ops Setup checklist, Decision 27's PJR Bridge move, and today's Agency/multi-store-first sequencing into one timeline.

| Phase | Timing | What gets built |
| --- | --- | --- |
| 0 | Before Week 1 | Ops setup: GitHub repo, Supabase project, Vercel project (env vars — no Doppler, Decision 33), GitHub Actions CI, Semgrep, Dependabot, Linear board |
| 1 | Weeks 1–3 | Foundation (expanded, Decision 36): multi-tenant schema (Owner → many Stores), Agency role + internal overview dashboard (stores/billing/overview, Decision 32), full role system (Agency/Owner/Manager/Cashier), "my stores" RLS scoping, store & employee setup, nav shell supporting single-store and network views, Sentry added (Decision 33) |
| 2 | Weeks 4–5 | Scan Engine + PJR Bridge: barcode scanner component, pack receive/activate, shift open/close scan, dual PIN sign-off, PJR Bridge desktop app built against the real captured samples (Appendix A) |
| 3 | Weeks 6–7 | Spot-Check System: selection algorithm, camera capture, photo upload, pass/fail flow, silent owner alert dispatch, Checkly added (Decision 33) |
| 4 | Weeks 8–9 | Tally & Reconciliation: manual entry, CSV import + parser, LSP scraper (pending Decision 28 credentials), cross-check logic, gap attribution |
| 5 | Weeks 10–11 | Dashboards & Alerts: Owner dashboard, network dashboard, cross-store employee pattern detection (moved up, Decision 34), SMS/push notifications, risk scoring, complaint logging |
| 6 | Weeks 12–13 | Polish & Pilot Launch: onboarding wizard (+ owner consent checkbox, Decision 37), employee consent interstitial (Decision 37), Office Staff role (moved up, Decision 35), mobile responsiveness audit, offline-mode foundation, staging environment setup (moved here, Decision 41), Better Uptime + dual outage escalation (Decision 39), pilot store goes live |
| 7 | Month 4+ | Remaining enhancements: email inbound parser, PDF incident reports, AI photo analysis, trend analytics, Zapier webhook |

# 7. What's Still Externally Blocked

The complete list. If it isn't here, it's decided in Sections 1–6 and ready to build against.

BLOCKED ON: Ticket barcode uniqueness Whether the lottery POSCode is ticket-unique or a generic game tag. Resolved on next pilot store visit (Appendix A, Section A.9, items 1–2). Blocks finalizing Decision 26's serial-parsing module only — scan capture itself is not blocked.

BLOCKED ON: Lottery MerchandiseCode value The department code Passport uses for lottery at the pilot store. Resolved on next pilot store visit (Appendix A, Section A.9, item 1). Blocks the PJR filter logic in Phase 2 only.

BLOCKED ON: LSP portal credentials Needed for the LSP scraper (Decision 28, Phase 4). Action owner: Farheen, via pilot store owner, next visit.

BLOCKED ON: Verifone file-access equivalent Only relevant once a Verifone pilot store is added — not a blocker for MVP, which is scoped to the Gilbarco pilot (Decision 25).

# 8. Immediate Next Actions (This Week)

- Start Phase 0 ops setup (revised tool list, Decision 33) — none of it depends on any open item.

- Start Phase 1 schema build in parallel — now scoped as multi-tenant (Owner → many Stores) with Agency role from the outset (Decision 32). The base schema in the Master Document (Section 05) still applies; it needs the multi-store relationship added before implementation, not after.

- Schedule the next pilot store visit to close out Section 7's blocked list: barcode uniqueness, MerchandiseCode, and LSP credentials in one trip.

- Once Phase 1 is stable, begin Phase 2 (Scan Engine + PJR Bridge) — the PJR parser can be built immediately against the three real sample files already in hand (Appendix A), without waiting for the store visit.

End of document.